## Sheet1
Dealsy Sprint 3 Burndown Chart
User Story | Start Hours | Hours Spent - Day 1 | Hours Spent - Day 2 | Hours Spent - Day 3 | Hours Spent - Day 4 | Hours Spent - Day 5 | Hours Spent- Day 6 | Hours Spent - Day 7 | Total Hours
As a customer I want to see product brands so that I can shop for the brand I want#25 | 2 |  |  | 1 |  |  | 1 |  | 2
As a customer I want to see the shipping price so that I can see if I am getting free shipping or decide if its worth paying#26 | 1 | 1 | [6 empty] | 1
As a customer, I want to be able to click on the link of the store and see the product. #28 | 2 |  | 3 |  | 2 | 2 |  |  | 7
As a customer I want to see product rating so that I can buy good product #30 | 1 |  |  |  |  | 1 |  |  | 1
Actual Remaining Hours | 6 | 5 | 2 | 1 | -1 | -4 | -5 | -5
Estimated Remaining Hours | 6 | 5.1429 | 4.2857 | 3.4286 | 2.5714 | 1.7143 | 0.85714 | 0