## Sprint 1 Burndown Chart
Dealsy Sprint 1 Burndown Chart
User Story | Start Hours | Hours Spent - Day 1 | Hours Spent - Day 2 | Hours Spent - Day 3 | Hours Spent - Day 4 | Hours Spent - Day 5 | Hours Spent- Day 6 | Hours Spent - Day 7 | Total Hours
As a user, I want to view the Home Screen so that it is easy to use. #23 | 5 | 2 |  | 2 |  |  |  | 1 | 5
As a customer, I would like to view categories of items so that I can browse a specific type of item. #10 | 5 | 3 |  |  |  |  | 2 |  | 5
As a customer, I want to be able to click on the product and let it redirect to stores website so I can view that product. #8 | 2 |  |  |  | 1 | 1 |  |  | 2
As a customer, I want to data from various store to see which store has best deal. #11 | 6 |  |  | 2 | 3 |  |  | 4 | 9
Actual Remaining Hours | 18 | 13 | 13 | 9 | 5 | 4 | 2 | -3
Estimated Remaining Hours | 18 | 15.4286 | 12.8571 | 10.2857 | 7.7143 | 5.1429 | 2.5714 | 0